# COCOMO Cost Estimation Report

Salary Pro Salary Management System

# 1 Project Overview

Salary Pro is a full stack salary management system developed using React, Tailwind CSS, Node.js, Express, and MongoDB. The system provides user authentication, role based access, employee management, attendance tracking, leave management, salary calculation, payslip generation, reports, settings, and salary insights.

This report estimates the software development effort, time, staffing, and cost using the Basic COCOMO model. The estimate is based on the verified source code count from the frontend and backend application files.

# 2 Project Size Estimation

| Source area | Files | Lines of code |
| --- | --- | --- |
| Frontend client src | 23 | 381 |
| Backend server src | 22 | 419 |
| Total application source | 45 | 800 |

The project size used for COCOMO is calculated as follows:

KLOC = Total LOC / 1000 = 800 / 1000 = 0.8 KLOC

Third party dependencies, node_modules, lock files, generated files, and diagrams are excluded from the source code count.

# 3 Chosen COCOMO Project Category

The Organic category is selected because Salary Pro is a relatively small academic web application developed by a small team using familiar technologies and clearly defined business requirements.

| COCOMO category | a | b | c | d |
| --- | --- | --- | --- | --- |
| Organic | 2.4 | 1.05 | 2.5 | 0.38 |

# 4 COCOMO Estimation Calculations

## 4.1 Effort Estimation

Formula: Effort = a x (KLOC)^b

Effort = 2.4 x (0.8)^1.05 = 1.90 person months

## 4.2 Development Time Estimation

Formula: Development Time = c x (Effort)^d

Development Time = 2.5 x (1.90)^0.38 = 3.19 months

## 4.3 Average Team Size

Formula: Average Team Size = Effort / Development Time

Average Team Size = 1.90 / 3.19 = 0.60, approximately 1 person

# 5 Cost Estimation

For this academic estimate, the assumed development cost is Rs 20,000 per person month.

| Cost item | Calculation | Result |
| --- | --- | --- |
| Estimated effort | 2.4 x (0.8)^1.05 | 1.90 person months |
| Cost per person month | Assumed rate | Rs 20,000 |
| Estimated cost | 1.90 x Rs 20,000 | Rs 38,000 |

# 6 Final Estimation Summary

| Metric | Estimated value |
| --- | --- |
| Project size | 800 LOC or 0.8 KLOC |
| Chosen project category | Organic |
| Estimated effort | 1.90 person months |
| Estimated development time | 3.19 months |
| Average COCOMO team size | Approximately 1 person |
| Actual academic team size | 3 members |
| Assumed cost per person month | Rs 20,000 |
| Estimated project cost | Rs 38,000 |

# 7 Conclusion

Using the Basic COCOMO Organic model, the Salary Pro system with 800 LOC is estimated to require 1.90 person months of effort and 3.19 months of development time. At an assumed cost of Rs 20,000 per person month, the estimated total cost is Rs 38,000. The project was completed by three students who can work in parallel on frontend, backend, database, testing, documentation, and deployment tasks. The COCOMO staffing value is an estimation based on code size and does not replace the actual academic team allocation.